## Hoja 1
Desglose		TAREAS	RECURSOS				SEMANA 1					SEMANA 2					SEMANA 3					SEMANA 4					SEMANA 5

			Jorge	Jimena	Daniel	Jaime	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V	S	D	L	M	X	J	V
T0	1	Cordinación Semanal
T1	1	Character: Campo following		X				JS
T1	2	Character: Nuevas funciones		X				JS	JS	JS
T1	3	Character: print		X					JS	JS
T1	4	Character: Documentar		X				JS	JS	JS	JS
T2	1	Game actions: abandon	X				JM	JM
T2	2	Game actions: recruit	X					JM	JM
T2	3	Game actions: Modificar Attack	X					JM	JM
T2	4	Game actions: Modificar move (Up)			X					D	D
T2	5	Game actions: Modificar move (Down)			X					D	D
T2	7	Game actions: Use			X					D	D
T2	8	Game actions: Open			X					D	D
T2	9	Documentar	X		X		JM	JM	JM	JM	D	D	D	D	D
T3	1	Command: recruit	X				JM	JM
T3	2	Command: abandon	X					JM	JM
T3	3	Command: Use					D	D
T3	4	Command: Open					D	D
T3	5	Command: Documentar	X		X		JM	JM	JM					D	D
T4	1	Set: Modificar para nuevos comandos			X					D	D	D
T5	1	Space: Modificar para nuevos comandos			X					D	D	D
T6	1	Game: Modificar para nuevos comandos			X					D	D	D
T7	1	Object: Vida				X		JR	JR
T7	2	Object: Movible				X		JR	JR
T7	3	Object: Dependencia				X		JR	JR
T7	4	Object: Abre				X			JR	JR
T7	5	Object: Modificar funciones				X				JR	JR
T7	6	Object: Modificar comandos				X				JR	JR	JR
T7	7	Object: Documentar				X		JR	JR	JR	JR	JR	JR
T8	1	anthill: Modificar fichero de datos				X					JR	JR
T9	1	Visualizacion del juego				X					D	D	D
T10	1	Fichero datos nuevo (libre)				X					JR	JR	JR	JR	JR	JR	JR	JR
T11	1	Documentación de usuario		X					JS	JS
T11	2	Descripción argumento juego		X					JS	JS	JS
T11	3	Información utilización juego		X					JS	JS
T11	4	Mapa		X					JS	JS
T11	5	Indicaciones a un final		X					JS	JS	JS
T11	6	Fichero acciones de las indicaciones		X					JS	JS	JS
T12	1	GameManagement: crear módulo				X					JR
T12	2	Managment: reemplazar a gameReader				X					JR	JR	JR
T12	3	Managment: funciones save y load				X					JR	JR	JR
T12	4	Managment: Documentar				X					JR	JR	JR	JR
T13	1	Command: save y load			X					JR	JR
T13	2	Game actions: funciones save y load			X					D	D	D
T13	3	Game actions: Documentar			X					D	D	D
T14	1	Rules: Crear módulo	X					JM	JM
T14	2	Rules: Funcione rules (min 6)	X					JM	JM	JM
T14	3	Rules: funcion run todas funciones	X					JM	JM	JM	JM	JM
T14	4	Rules: Documentar	X					JM	JM	JM	JM
T15	1	Juego determinista	X					JM	JM	JM	JM	JM	JM
T16	1	Game Loop: condición cambiar turno			X					D	D					-
T16	2	Game Loop: documentar			X					D	D
T17	1	Command: "cooperar" (analoga "recruit)	X		X					JM	D
T17	2	Game actions: función "cooperar"	X		X					D	D	JM	JM
T17	3	Game actions: Documentar	X		X					JM	JM	D	D
T18	1	Game loop: log, añadir jugador				X					JR	JR
T19	1	Tests: Space				X					JR	JR
T19	2	Test: Object				X					JR	JR	JR	JR
T19	3	Tests: Player				X					JR	JR	JR	JR
T19	4	Tests: Set				X					JR	JR	JR
T19	5	Tests: Character		X					JS	JS	JS
T19	6	Tests: Link		X					JS	JS
T19	7	Tests: Inventory		X					JS	JS
T19	8	Tests: Bash Script		X					JS	JS	JS	JS
T19	9	Tests: Pruebas Automáticas		X					JS	JS	JS
T20	1	Makefile	X	X	X	X
T21	1	Depuración de errores	X	X	X	X
T22	1	Revisión general	X	X	X	X
T23	1	Entrega				X